## Slide 1
Solving Real Bottlenecks
in Corrugated Plants
Industrial Intelligence Applied to Performance
PSC VISALIA PROJECT | Complete Relocation + Modernization + Automation
INGECART | LINETEX USA | PACIFIC SOUTHWEST CONTAINER

## Slide 2
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Solving Real Bottlenecks in Corrugated Plants
Industrial Intelligence Applied to Performance
1
FASTER THAN OEMs
Agile engineering and
rapid implementation
2
MORE RELIABLE
Robust solutions built
to perform
3
MEASURABLE ROI
Focus on what impacts
your OEE
4
KNOWLEDGE DRIVEN
Every project makes
us smarter

## Slide 3
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Executive Summary – Turnkey Project
PROJECT OVERVIEW:
• Relocate BHS corrugator (1997, Turkey → Visalia, California)
• Complete obsolescence elimination (Siemens S5 → S7)
• Full downstream automation: Ingetrans, Conveyors, AMR, WIP buffer
INVESTMENT: ~$7M USD
KEY IMPACT METRICS:
• -70% downtime risk from obsolescence
• +20% sustained speed (250 → 300 mpm)
• MES/ERP-ready platform
• Estimated payback: <18 months
"Not just moving a machine – transforming the operation"

## Slide 4
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Why This Project? – Strategic Necessity
ELIMINATE OBSOLESCENCE:
• Current S5 PLC – No factory support since 2015
• Critical spare parts unavailable in global market
• Weeks of unplanned downtime risk
INCREASE PRODUCTIVITY:
• Sustained 300 mpm vs current 250 mpm
• Real-time diagnostics and predictive maintenance
• Estimated 30% setup time reduction
PREPARE FOR THE FUTURE:
• Open Siemens S7 architecture
• MES/ERP integration ready
• Foundation for full AMR/WIP automation

## Slide 5
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Ingecart by the Numbers
1,268
Projects Completed
28
Years of Experience
26
International Agreements
194
Installations

## Slide 6
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Obsolescence Elimination – Siemens S7 Migration
BEFORE (Current State in Turkey):
• Mixed S5/S7 control architecture
• No factory support for S5
• DC drives with obsolete components
• Legacy HMI with limited diagnostics
• Spare parts unavailable globally
• High risk of extended downtime
AFTER (Installed in Visalia):
• Unified Siemens S7 – 15+ year future
• Full factory support and updates
• Modern AC drives + motion control
• Touchscreen HMI + SCADA ready
• Global spare parts availability
• Predictive maintenance capable

## Slide 7
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Project Scope – 4 Integrated Phases
PHASE 1: DISASSEMBLY (Turkey)
→ Complete teardown + component tagging + preservation for transport
PHASE 2: TRANSPORT (Turkey → Visalia)
→ 11 Open top + 2 Flat rack + 16 HQ 40' containers
→ Full packaging and export documentation
PHASE 3: REINSTALLATION (Visalia)
→ Mechanical assembly + laser alignment + peripheral connection
PHASE 4: MODERNIZATION + INTEGRATION
→ Siemens S7 + new drives + HMI
→ Conveyors + AMR + Ingetrans + WIP buffer

## Slide 8
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Ingetrans – Automated Roll Loading System
CAPABILITIES:
• Automatic roll loading up to 3,700 mm diameter
• No forklift intervention – improved safety
• Integrated loading/unloading ramp system
• Double transfer car + rails + catenary system
• Complete electrical cabinets + proprietary software
• Assembly + 4 x 40' containers transport included
INVESTMENT: $1.14M USD (sale price)
"Reduced manual handling + increased operational safety"

## Slide 9
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Conveyors & AMR – Intelligent Material Flow
SYSTEM COMPONENTS:
• Double output line with integrated strappers → $900K
• AMR reception conveyor + waste movement → $550K
• Intelligent WIP buffer between corrugator and converting
• Full integration with existing AAR stacker
OPERATIONAL BENEFITS:
• Continuous flow to converting area
• No accumulation stoppages
• Real-time production tracking
"The corrugator never stops due to downstream accumulation"

## Slide 10
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Measurable ROI – Focus on OEE
QUANTIFIABLE BENEFITS:
• Downtime reduction from obsolescence: -70%
• Sustained speed increase: 250 → 300 mpm (+20%)
• Setup time reduction: -30%
• Unplanned stops from parts unavailability: ELIMINATED
• Maintenance cost reduction: -25%
• Energy efficiency improvement: -15% (new drives)
ESTIMATED PAYBACK: <18 MONTHS
TOTAL INVESTMENT: ~$7M USD (equipment + services + engineering)
"Focus on what impacts your OEE"

## Slide 11
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Project Timeline – ~9 Months
Engineering + FAT: ████████ 8 weeks
→ Detailed design, software development, factory testing
Disassembly (Turkey): ████ 4 weeks
→ On-site teardown, tagging, container loading
Shipping (Turkey → Visalia): ██████ 6 weeks
→ Ocean freight, customs clearance, delivery
Mechanical Reinstallation: ████████ 8 weeks
→ Assembly, alignment, mechanical integration
Electrical Modernization + Software: ██████ 6 weeks
→ S7 installation, drives, HMI, commissioning
Site Acceptance Test + Ramp-up: ████ 4 weeks
→ Validation, training, production handover
TOTAL ESTIMATED: 36 weeks

## Slide 12
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Quality Assurance – FAT & SAT Process
FACTORY ACCEPTANCE TEST (FAT):
• Conducted at Ingecart partner facilities before shipping
• Full software and control system validation
• Customer witness opportunity
SITE ACCEPTANCE TEST (SAT):
• Conducted at PSC Visalia after installation
• Performance validation against KPIs
• Joint sign-off with customer team
POST-COMMISSIONING SUPPORT:
• 2 weeks intensive on-site support
• Remote diagnostics and monitoring
• 24/7 emergency response availability

## Slide 13
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Investment Summary
BHS CORRUGATOR (reused equipment): $950K
SERVICES (disassembly, transport, installation, PM): $1.2M
PERIPHERALS (Flexamix kitchen, boiler, steam piping): $1.1M
CONVEYORS + AMR SYSTEM: $1.45M
INGETRANS (automated loading system): $1.32M
CIVIL WORK + PERMITS (estimated): $900K
TOTAL ESTIMATED INVESTMENT: ~$6.92M USD
PROPOSED PAYMENT STRUCTURE:
• 30% with Purchase Order
• 30% upon installation start
• 30% upon commissioning
• 10% upon SAT completion

## Slide 14
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Why Ingecart + Linetex?
✓ REAL CORRUGATED EXPERIENCE
→ Dozens of projects across Europe and USA
→ 65+ corrugated plants in Spain (AFCO ecosystem)
✓ TRUE TURNKEY APPROACH
→ Single point of responsibility from disassembly to production
→ No finger-pointing between vendors
✓ PROVEN AMR INTEGRATION
→ Not theoretical – we make it work in production environments
✓ LOCAL USA SUPPORT
→ Linetex as local agent + available engineers
→ Rapid response times
✓ VERIFIED REFERENCES
→ International Paper, Saica, DS Smith, Smurfit WestRock, Hinojosa
"Faster than OEMs · More reliable than low-cost"

## Slide 15
SOLUTIONS DESIGNED FOR CORRUGATED PLANTS
Next Steps
IMMEDIATE ACTIONS:
1. Layout validation – Onsite or remote technical meeting
2. Final scope definition – Detailed engineering confirmation
3. Final economic proposal – With signatures
4. Engineering start – 8 weeks before disassembly
5. Financing plan discussion – If applicable
CONTACTS:
• Diego Garcia (Ingecart) – Technical & Commercial Director
diego@ingecart.eu
• Linetex USA – Local Agent & Contractual Support
• Enrique Verduzco (PSC) – Technical Counterpart

## Slide 16
Solving Real Bottlenecks
in Corrugated Plants
Industrial Intelligence Applied to Performance
Thank You | Q&A
Diego Garcia | diego@ingecart.eu | ingecart.eu
Linetex USA | Local Support